## Sheet1
BOM ITEM NUMBER | CUSTOMER RFQ/Stock Number | ASSEMBLY | Level | DWG/PART NO. | REV | FAB LEVEL | DESCRIPTION | Qty Needed for PO | U of M | Qty on Hand | PUR QTY | COST EACH | COST TOTAL | VENDOR | MFG | COMMENTS | QUOTE | QUOTE DATE | RELEASE FOR PURCHASE DATE | ORDER DATE | PROM DEL DATE | REV DEL DATE | DATE RECEIVED | P O # | PARTS INSPECTED (X) | DAYS UNTIL DUE OR DAYS EARLY (blue) / DAYS OVER DUE OR DAYS LATE (red) | COMMENTS | MAKE/BUY | VENDOR 1 AXIS | COST EACH | COST TOTAL | VENDOR 2 CUSTOM | COST EACH | COST TOTAL | VENDOR 3 IME | COST EACH | COST TOTAL | COMMENTS
[7 empty] | TOTAL | [5 empty] | #REF! | [17 empty] | #REF! |  |  | #REF! |  |  | #REF!
| R-1 | ROBOT | 1 | C01871D | S |  | CECIL ROBOT | 1 |  |  | 1 |  | 0 |  | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
1 | R-1.1 | C01871D | 2 | C01872-1 | J |  | ASSEMBLY, LOCOMOTION | 1 | EA |  |  |  | 0 |  | QNA | C01872D-1 in DWG | [14 empty] | 0 |  |  | 0 |  |  | 0
1 | R-1.1.2 | C01872-1 | 3 | C01876D | F1 |  | Locomotion Potentiometer Assembly | 1 | EA |  | 1 |  | 0 |  | QNA | [12 empty] | MAKE |  |  | 0 |  |  | 0 |  |  | 0
1 | R-1.1.2.3 | C01876D | 4 | C01571C | D |  | Potentiometer Bracket | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
2 |  | C01876D | 4 | B1-27 | A |  | .125W .375OD .187ID Ball Bearing | 2 | EA |  | 2 | 55.54 | 111.08 | MOTION INDUSTRIES | WM Berg | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
3 |  | C01876D | 4 | C01575B | B |  | Idler Shaft | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
4 |  | C01876D | 4 | C01577B | B |  | Idler Spur Gear Modification | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
5 |  | C01876D | 4 | C01573B | B |  | Potentiometer Drive Shaft | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
6 |  | C01876D | 4 | 5100-18 |  |  | External Retention Ring | 1 | 100 PK |  | 1 |  | 0 | TRU ARC | TRU ARC | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
7 | R-1.1.2.2 | C01876D | 4 | C01572B | B |  | Modified Miter Gear | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
8 |  | C01572B | 5 | C01576B | A |  | POT Idler gear Spacer | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
9 | R-1.1.2.1 | C01876D | 4 | 20M1765 |  |  | 10 Turn Potentimeter | 1 | EA |  | 1 | 245.36 | 245.36 | NEWARK | VISHAY |  |  | 2025-06-18 | [9 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
10 |  | C01876D | 4 | C01580B | B |  | Potentiometer Sleeve | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
11 |  | C01876D | 4 | C01578B | A |  | Knurled Wheel | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
12 |  | C01876D | 4 | C0240-032-0310-S |  |  | .31 LG .032 Wire .24OD Spring | 1 | EA |  | 1 | 1.98 | 1.98 | MOTION INDUSTRIES | Asso. Spring | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
13 |  | C01876D | 4 | C01581B | B |  | POT Spur Gear Modification | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
14 |  | C01876D | 4 | C01579B | A |  | Washer | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
15 |  | C01876D | 4 | C01574B | C |  | Pinion Shaft Modification | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
16 |  | C01876D | 4 | C03915 | B |  | Bearing Modified | 1 | EA |  | 1 |  | 0 | IME | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
17 |  | C01876D | 4 | 92196A112 |  |  | 18-8 Stainless Steel Socket Head Screw 4-40 Thread Size, 5/8" Long | 2 | 100 PK |  | 1 |  | 0 | McMaster | [13 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
18 |  | C01876D | 4 | 271 |  |  | Thread Locking Compound | 0 | A/R |  | 0 |  | 0 | [14 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
19 |  | C01876D | 5 | CTA4-IS-60 |  |  | Strip Connector | 1 | EA |  | 1 |  | 0 | Digi-Key | ITT Cannon | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
20 |  | C01876D | 4 | 030-9542-001 |  |  | SOCKET, CONNECTOR | 3 |  |  |  |  | 0 |  | ITT CANNON | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
21 |  | C01876D | 4 | 7054/19 BK005 |  |  | HOOK-UP STRND 24AWG BLACK 100' 19/36 | A/R | 100 FT | PLTY | A/R | 83.3 | #VALUE! | DIGIKEY | ALPHA WIRE |  |  | 2025-06-17 | [9 empty] | BUY |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE!
22 |  | C01876D | 4 | 7054/19 BL005 |  |  | HOOK-UP STRND 24AWG BLACK 100' 19/36 | A/R | 100 FT | PLTY | A/R | 81.64 | #VALUE! | DIGIKEY | ALPHA WIRE |  |  | 2025-06-17 | [9 empty] | BUY |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE!
23 |  | C01876D | 4 | 7054/19 OR005 |  |  | HOOK-UP STRND 24AWG BLACK 100' 19/36 | A/R | 100 FT | PLTY | A/R | 83.3 | #VALUE! | DIGIKEY | ALPHA WIRE |  |  | 2025-06-17 | [9 empty] | BUY |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE!
24 |  | C01876D | 4 | 4024 |  |  | URETHANE A-85 | A/R | 100 PK |  | A/R |  | #VALUE! |  | HARDMAN | [12 empty] | BUY |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE!
25 |  | C01876D | 4 | LC134 BK088 (LC134 Obsolete) |  |  | TAPE, LACING | A/R | 1500 FT | PLTY | A/R | 113.66 | #VALUE! | DIGIKEY | ALPHA |  |  | 2025-06-17 | [9 empty] | BUY |  |  | #VALUE! |  |  | #VALUE! |  |  | #VALUE!
2 | R-1.1.1 | C01872D | 3 | C01877D | F |  | ASSY/LOCOMOTION DRIVE MOTOR | 1 |  |  |  |  | 0 |  | QNA | [12 empty] | MAKE |  |  | 0 |  |  | 0 |  |  | 0
1 | R-1.1.1.1 | C01877D | 4 | 1000006622 |  |  | 3557K024CR+38/2S66:1+BRK01+MG10+X0497 | 1 | EA |  | 1 |  | 0 | FAULHABER | FAULHABER | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
2 | R-1.1.1.3 | C01877D | 4 | C01586B | A |  | Gear, Miter, Motor (modified) | 1 | EA |  | 1 |  | 0 | CUSTOM | QNA |  | 403568 | [13 empty] | 0 |  |  | 0 |  |  | 0
3 | R-1.1.1.2 | C01877D | 4 | C01588D | D |  | Motor Support Bracket | 1 | EA |  |  |  | 0 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
4 | R-1.1.1.4 | C01877D | 4 | C01593B | C |  | Motor Carriage Guide Bar | 2 | EA |  |  |  | 0 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
5 |  | C01877D | 4 | 90145A440 |  |  | Dowel Pin, .093" dia x .63" LG | 1 | 50 pk |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
6 |  | C01877D | 4 | 91292A112 |  |  | Screw, M3 X 8 LG, SHCS | 4 | 100 pk |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C01877D | 4 | 91771A076 |  |  | Screw, 2-56 UNC x .15 LG, FHP | 3 | 100 pk |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
8 |  | C01877D | 4 | 91771A105 |  |  | Screw, 2-56 UNC x .38 LG, FHP | 3 | 100 pk |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C01877D | 4 | 242 |  |  | Threadlocker | AR | EA |  |  | 18.8 | 0 | McMaster | Loctite |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C01877D | 4 | V56ZA2 (V56ZA2PX2855-ND) |  |  | Varistor | 1 | EA | 51 | 0 | 0.11 | 0 | ARROW | Littlefuse |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C01877D | 4 | IN4004-E3/54 |  |  | Diode | 1 | EA |  |  | 0.16 | 0 | DigiKey | Vishay |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C01877D | 4 | 03-06-2042 |  |  | Plug | 1 |  |  |  | 0.4 | 0 | DigiKey | Molex |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
13 |  | C01877D | 4 | 02-06-6103 |  |  | Pin | 4 | EA |  |  | 0.71 | 0 | DigiKey | Molex |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
14 |  | C01877D | 4 | TFE 20 AWG |  |  | Teflon Sleeve | AR | A/R |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
15 |  | C01877D | 4 | TFE 22 AWG |  |  | Teflon Sleeve | AR | A/R |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
16 |  | C01877D | 4 | 2328-22UL1429STRRED100-ND |  |  | Wire, 22 AWG, 19/34 RED | 1 | 100 FT |  |  | 34.25 | 0 | DigiKey | Remington Industries |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
17 |  | C01877D | 4 | 2328-22UL1429STRBLA100-ND |  |  | Wire, 22 AWG, 19/34 BLK | 1 | 100 FT |  |  | 34.25 | 0 | DigiKey | Remington Industries |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
18 |  | C01877D | 4 | 24UL1429STRWHI100 |  |  | Wire, 24 AWG, 19/36 WHT | 1 | 100 FT |  |  | 30.16 | 0 | DigiKey | Remington Industries |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
21 |  | C01877D | 4 | LC134BK088-ND |  |  | Lacing Tape (Roll) | 1 | EA |  |  | 117.56 | 0 | NEWARK | Alpha Wire |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
22 |  | C01877D | 4 | C02660B-1 | B |  | Motor Bracket Shim | 1 | EA |  |  |  | 0 | CUSTOM | QNA |  | 403568 | [13 empty] | 0 |  |  | 0 |  |  | 0
23 |  | C01877D | 4 | C02660B-2 | B |  | Motor Bracket Shim | 1 | EA |  |  |  | 0 | CUSTOM | QNA |  | 403568 | [13 empty] | 0 |  |  | 0 |  |  | 0
24 |  | C01877D | 4 | C02660B-3 | B |  | Motor Bracket Shim | 1 | EA |  |  |  | 0 | CUSTOM | QNA |  | 403568 | [13 empty] | 0 |  |  | 0 |  |  | 0
25 |  | C01877D | 4 | C02660B-4 | B |  | Motor Bracket Shim | 1 | EA |  |  |  | 0 | CUSTOM | QNA |  | 403568 | [13 empty] | 0 |  |  | 0 |  |  | 0
26 |  | C01877D | 4 | C02660B-5 | B |  | Motor Bracket Shim | 1 | EA |  |  |  | 0 | CUSTOM | QNA |  | 403568 | [13 empty] | 0 |  |  | 0 |  |  | 0
3 | R-1.1.3 | C01872D | 3 | C01878B | E |  | ASSY, DRIVE SHAFT | 1 | EA |  |  |  | 0 | [14 empty] | MAKE |  |  | 0 |  |  | 0 |  |  | 0
1 | R-1.1.3.4 | C01878B | 4 | C01582B | F |  | SHAFT, DRIVE | 1 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
2 | R-1.1.3.1 | C01878B | 4 | C01584B | B |  | GEAR, MITER, DRIVE SHAFT (MODIFIED) | 1 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
3 | R-1.1.3.5 | C01878B | 4 | C01583B | B |  | GEAR, SPUR (MODIFIED) | 1 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
4 | R-1.1.3.6 | C01878B | 4 | C01585B | B |  | SPACER, GEAR | 1 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
5 | R-1.1.3.7 | C01878B | 4 | C01894B | A |  | SPACER, DRIVE SHAFT | 1 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
6 |  | C01878B | 4 | C01912B | A |  | KEY | 2 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
7 | R-1.1.3.3 | C01878B | 4 | 91580A151 |  |  | Internal Retaining Ring 15-7 PH Stainless Steel, for 1/2" ID | 2 | 10 pk |  | 1 | 14.85 | 14.85 | McMaster | McMASTER-CARR | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
8 | R-1.1.3.2 | C01878B | 4 | 7Y55-PS5025 |  |  | BEARING, BALL, .25 BORE | 2 |  |  |  |  | 0 |  | SDP | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
9 |  | C01878B | 4 | 92311A074 |  |  | 18-8 Stainless Steel Cup-Point Set Screw 2-56 Thread, 1/8" Long | 1 |  |  |  |  | 0 | McMaster | [13 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
10 |  | C01878B | 4 | 92311A073 |  |  | 18-8 Stainless Steel Cup-Point Set Screw 2-56 Thread, 3/32" Long | 1 |  |  |  |  | 0 | McMaster | [13 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
11 | R-1.1.3.3 | C01878B | 4 | 91590A113 |  |  | ForwardPrintIs this page helpful? External Retaining Ring for 1/4" OD, 15-7 PH Stainless Steel | 1 |  |  |  |  | 0 | McMaster | [13 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
4 |  | C01872D | 3 | C01879B | A |  | ASSY, STABILIZER ARM | 4 |  |  |  |  | 0 |  | QNA | [12 empty] | MAKE |  |  | 0 |  |  | 0 |  |  | 0
1 |  | C01879B | 4 | C01589C | B |  | ARM, STABILIZER | 4 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
2 |  | C01879B | 4 | C01591B | A |  | PIN, STABILIZER WHEEL | 4 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
3 |  | C01879B | 4 | C01592B | A |  | WHEEL, STABILIZER | 4 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
4 |  | C01879B | 4 | C01590B | B |  | PIN, STABILIZER ARM | 4 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
5 |  | C01879B | 4 | 7Y55-PSS3118 |  |  | BEARING, BALL, 3/16 BORE | 4 |  |  |  |  | 0 |  | SDP | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
6 |  | C01879B | 4 | 5100-18-BC |  |  | RING, RETAINING | 4 |  |  |  |  | 0 |  | WALDES | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
5 | R-1.1.5 | C01872D | 3 | C01880C-1 | C |  | ASSY, LOCOMOTION DISENGAGEMENT | 1 |  |  |  |  | 0 | [14 empty] | MAKE |  |  | 0 |  |  | 0 |  |  | 0
1 |  | C01880C-1 | 4 | C01596C | A |  | BLOCK, MOTOR DISENGAGE | 1 | EA |  | 1 | 701 | 701 | AXIS | QNA | RFQ sent 6/6 | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
2 |  | C01880C-1 | 4 | C01808B | A |  | HANDLE, MOTOR, DISENGAGE | 1 | EA |  | 1 | 518 | 518 | AXIS | QNA | RFQ sent 6/6 | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
3 |  | C01880C-1 | 4 | C01809C | A |  | ROD, MOTOR DISENGAGE | 1 | EA |  | 1 | 1805.85 | 1805.85 | AXIS | QNA | RFQ sent 6/6 | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
4 |  | C01880C-1 | 4 | C01598C | A |  | LINK, SHORT ROUND | 1 | EA |  | 1 | 585 | 585 | AXIS | QNA | RFQ sent 6/6, better price IME | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
5 |  | C01880C-1 | 4 | C01594B | A |  | LINK, SHORT | 1 | EA |  | 1 | 740 | 740 | AXIS | QNA | RFQ sent 6/6, better price IME | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
6 |  | C01880C-1 | 4 | C01595B | A |  | LINK, UPPER | 1 | EA |  | 1 | 748 | 748 | AXIS | QNA | RFQ sent 6/6 | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C01880C-1 | 4 | C01597B | B |  | LINK, FLAT | 1 | EA |  | 1 | 493 | 493 | AXIS | QNA | RFQ sent 6/6 | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
8 |  | C01880C-1 | 4 |  |  |  | ROLL PIN, 1/16"Ø x 1/8" lg | 1 |  |  |  |  | 0 |  |  | NEED TO FIND PART | [14 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C01880C-1 | 4 | 90145A416 |  |  | 18-8 Stainless Steel Dowel Pin 1/16" Diameter, 5/16" Long | 1 | 100 PK |  | 1 | 9.98 | 9.98 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C01880C-1 | 4 | 92196A054 |  |  | 18-8 Stainless Steel Socket Head Screw 0-80 Thread Size, 3/16" Long | 1 | 100 pk |  | 1 | 8.57 | 8.57 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C01880C-1 | 4 | 92196A148 |  |  | 18-8 Stainless Steel Socket Head Screw 6-32 Thread Size, 1/2" Long | 2 | 100 pk |  | 1 | 7.62 | 7.62 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C01880C-1 | 4 | C01807B | A |  | KNOB, DISENGAGE | 1 | EA |  | 1 | 467 | 467 | AXIS | QNA | RFQ sent 6/6 | 27678 | 2024-07-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C01872D | 3 | C01567E | H |  | HOUSING, LOCOMOTION, ROBOT | 1 | EA |  |  |  | 0 |  | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
8 |  | C01872D | 3 | C01568C-1 | A |  | AXLE, WHEEL | 1 | EA |  |  |  | 0 |  | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C01872D | 3 | C01568C-2 | A |  | AXLE, WHEEL | 1 | EA |  |  |  | 0 |  | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C01872D | 3 | C01568C-3 | A |  | AXLE, WHEEL | 1 | EA |  |  |  | 0 |  | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C01872D | 3 | C01568C-4 | A |  | AXLE, WHEEL | 1 | EA |  |  |  | 0 |  | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C01872D | 3 | C01569B-1 | B |  | BUSHING, WHEEL AXLE | 2 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
13 |  | C01872D | 3 | C01569B-2 | B |  | BUSHING, WHEEL AXLE | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
14 |  | C01872D | 3 | C01569B-3 | B |  | BUSHING, WHEEL AXLE | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
15 |  | C01872D | 3 | C01570B | A |  | GUIDE WHEEL, FLAT | 2 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
16 |  | C01872D | 3 | C01587B | A |  | SPACER | 1 |  |  |  |  | 0 |  | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
18 |  | C01872D | 3 | 242 |  |  | THREADLOCKING ADHEIVE | A/R |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
19 |  | C01872D | 3 | C0420-063-1000-S |  |  | SPRING,, .420 O.D Ø .063 WIRE, 1.00 LG | 1 |  |  |  |  | 0 |  | SPEC | [15 empty] | 0 |  |  | 0 |  |  | 0
20 |  | C01872D | 3 | 5100-18-BC |  |  | RING, RETAINING | 4 |  |  |  |  | 0 |  | WALDES | [15 empty] | 0 |  |  | 0 |  |  | 0
21 |  | C01872D | 3 | CL-43-SSPS-1 |  |  | PLUNGER, SPRING | 4 |  |  |  |  | 0 |  | CARR LANE | [15 empty] | 0 |  |  | 0 |  |  | 0
22 |  | C01872D | 3 | 94355A738 |  |  | 18-8 Stainless Steel Flat-Tip Set Screws 1/2"-13 Thread, 1/2" Long | 1 | EA |  | 1 | 2.83 | 2.83 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
23 |  | C01872D | 3 | B1-7 |  |  | BALL BEARING | 2 |  |  |  |  | 0 |  | BERG | [15 empty] | 0 |  |  | 0 |  |  | 0
24 |  | C01872D | 3 | A7Y16-IE |  |  | WHEEL, V | 2 |  |  |  |  | 0 |  | SDP | [15 empty] | 0 |  |  | 0 |  |  | 0
25 |  | C01872D | 3 | BR2 |  |  | LUBRICANT | A/R |  |  |  |  | 0 |  | DOW CORNING | [15 empty] | 0 |  |  | 0 |  |  | 0
26 |  | C01872D | 3 | A-7X-8-C06012 |  |  | SPACER, SHAFT, .012 | 4 |  |  |  |  | 0 |  | SDP | [15 empty] | 0 |  |  | 0 |  |  | 0
27 |  | C01872D | 3 | A-7X-8-C06014 |  |  | SPACER, SHAFT, .014 | 2 |  |  |  |  | 0 |  | SDP | [15 empty] | 0 |  |  | 0 |  |  | 0
28 |  | C01872D | 3 | A-7X-8-C06031 |  |  | SPACER, SHAFT, .031 | 1 |  |  |  |  | 0 |  | SDP | [15 empty] | 0 |  |  | 0 |  |  | 0
29 |  | C01872D | 3 | A-7X-8-C06063 |  |  | SPACER, SHAFT, .063 | 1 |  |  |  |  | 0 |  | SDP | [15 empty] | 0 |  |  | 0 |  |  | 0
30 |  | C01872D | 3 | A-7X-8-C06188 |  |  | SPACER, SHAFT, .188 | 1 |  |  |  |  | 0 |  | SDP | [15 empty] | 0 |  |  | 0 |  |  | 0
31 |  | C01872D | 3 | 271 |  |  | THREADLOCKING ADHEIVE | A/R |  |  |  |  | 0 |  | Loctite | [15 empty] | 0 |  |  | 0 |  |  | 0
2 | R-1.2 | C01871D | 2 | C01873D-3 | R |  | ASSEMBLY, TILT | 1 |  |  |  |  | 0 | [14 empty] | MAKE |  |  | 0 |  |  | 0 |  |  | 0
1 | R-1.2.1 | C01873D-3 | 3 | C01881D | H |  | ASSY, TILT MOTOR | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
1 |  | C01881D | 4 | 1000006476 |  |  | 3540K024C 38/2S 989:1 + X0430+X0497 | 1 |  |  | 1 | 967.2 | 967.2 | FAULHABER | FAULHABER | [15 empty] | 0 |  |  | 0 |  |  | 0
2 |  | C01881D | 4 | C01813C | E |  | Reducer Shaft | 1 |  |  |  |  | 0 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
3 |  | C01881D | 4 | C01814D | B |  | Tilt Motor Mount | 1 |  |  |  |  | 0 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
4 |  | C01881D | 4 | C01914B | A |  | Tilt Motor Cap | 1 |  |  |  |  | 0 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
5 |  | C01881D | 4 | 242 |  |  | THREADLOCKER | A/R |  |  |  |  | 0 |  | LOCTITE | [15 empty] | 0 |  |  | 0 |  |  | 0
6 |  | C01881D | 4 | C03244B | B |  | Modified Spur Gear | 1 |  |  |  |  | 0 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C01881D | 4 | 91292A112 |  |  | Screw, M3 X 8 LG, SHCS | 4 | 100 pk |  | 1 | 5.45 | 5.45 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
8 |  | C01881D | 4 | C03245B-2 | A |  | Key | 1 |  |  | 1 | 139.7864 | 139.7864 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C01881D | 4 | 91771A148 |  |  | Screw, 6-32 UNC x .50" LG, PHILLIPS, FHMS | 2 | 100 pk |  | 1 | 7.54 | 7.54 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C01881D | 4 | V56ZA2P |  |  | Varistor | 1 | EA |  | 1 | 0.56 | 0.56 | MOUSER | Littlefuse |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C01881D | 4 | 03-06-2023 |  |  | Plug | 1 | EA |  | 1 | 0.25 | 0.25 | NEWARK | Molex |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C01881D | 4 | 02-06-6103 |  |  | Pin | 2 | EA |  |  | 0.71 | 0 | MOUSER | Molex |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
13 |  | C01881D | 4 | 22UL1429STRBLA100 |  |  | Wire, 22 AWG, 19/34 BLACK | 1 | 100 FT |  | 1 | 34.25 | 34.25 | DigiKey | Remington Industries |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
14 |  | C01881D | 4 | 22UL1429STRRED100 |  |  | Wire, 22 AWG, 19/34 RED | 1 | 100 FT |  | 1 | 34.25 | 34.25 | DigiKey | Remington Industries |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
15 |  | C01881D | 4 | 4024 |  |  | A-85 Urethane | AR |  |  |  | 182.01 | 0 | ELLSWORTH | Hardman |  | 2025-06-18 | [13 empty] | 0 |  |  | 0 |  |  | 0
16 |  | C01881D | 4 | TFE 22 AWG |  |  | Teflon Sleeve | AR | 1 FT |  |  | 12.83 | 0 | Amazon | Cole Flex |  | 2025-06-17 | [13 empty] | 0 |  |  | 0 |  |  | 0
17 |  | C01881D | 4 | 92196A108 |  |  | Screw, 4-40 UNC x .38" LG, SHCS | 1 |  |  | 1 | 5.84 | 5.84 | McMaster | McMaster-Carr | [15 empty] | 0 |  |  | 0 |  |  | 0
18 |  | C01881D | 4 | 92311A073 |  |  | Screw, 2-56 UNC x .095 LG, Set, Hex Head | 1 |  |  | 1 | 13.86 | 13.86 | McMaster | McMaster-Carr | [15 empty] | 0 |  |  | 0 |  |  | 0
19 |  | C01881D | 4 | C03307B | A |  | Tilt Motor Key | 1 |  |  | 1 | 393.4008 | 393.4008 | IME | QNA |  | Q5635 | [13 empty] | 0 |  |  | 0 |  |  | 0
3 |  | C01873D-3 | 3 | C01879B | A |  | ASSY, STABILIZER ARM | 2 |  |  |  |  | 0 |  | QNA | [12 empty] | MAKE |  |  | 0 |  |  | 0 |  |  | 0
1 |  | C01879B | 4 | C01589C | B |  | ARM, STABILIZER | 2 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
2 |  | C01879B | 4 | C01591B | A |  | PIN, STABILIZER WHEEL | 2 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
3 |  | C01879B | 4 | C01592B | A |  | WHEEL, STABILIZER | 2 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
4 |  | C01879B | 4 | C01590B | B |  | PIN, STABILIZER ARM | 2 |  |  |  |  | 0 |  | QNA | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
5 |  | C01879B | 4 | 7Y55-PSS3118 |  |  | BEARING, BALL, 3/16 BORE | 2 |  |  |  |  | 0 |  | SDP | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
6 |  | C01879B | 4 | 5100-18-BC |  |  | RING, RETAINING | 2 |  |  |  |  | 0 |  | WALDES | [12 empty] | BUY |  |  | 0 |  |  | 0 |  |  | 0
4 |  | C01873D-3 | 3 | C01599E-1 | J |  | HOUSING, TILT | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
5 |  | C01873D-3 | 3 | C01803C | C |  | SHAFT, IDLER | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
6 |  | C01873D-3 | 3 | C01807B | A |  | KNOB, MOTOR DISENGAGE | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C01873D-3 | 3 | C01804B | A |  | GEAR, SPUR (MODIFIED) | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C01873D-3 | 3 | C01822C | C |  | GUIDE, FIXED | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C01873D-3 | 3 | C01805B | B |  | SPACER, GEAR, IDLER | 2 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C01873D-3 | 3 | C01817D | E1 |  | BARREL | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C01873D-3 | 3 | C01818B | A |  | BUSHING, TILT | 2 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
13 |  | C01873D-3 | 3 | C01806B | A |  | PLUG, IDLER SHAFT BORE | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
14 |  | C01873D-3 | 3 | C01820B | B |  | RETAINER, BEARING, TILT (INBOARD) | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
15 |  | C01873D-3 | 3 | C01819B | D |  | RETAINER, BEARING, TILT (OUTBOARD) | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
16 |  | C01873D-3 | 3 | 3408A96 |  |  | Slotted Spring Plunger with 440C Stainless Steel Ball-Nose 18-8 Stainless Steel Body, 1/4"-20 Thread, 2-4 lb. Nose Force | 3 | EA |  | 6 | 4.74 | 28.44 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
17 |  | C01873D-3 | 3 | 242 |  |  | THREADLOCKER | A/R |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
18 |  | C01873D-3 | 3 | LAO25XPO |  |  | BEARING, BALL, ANGULAR, CONTACT | 2 |  |  |  |  | 0 |  | KAYDON | [15 empty] | 0 |  |  | 0 |  |  | 0
19 |  | C01873D-3 | 3 | B-65 |  |  | BEARING, NEEDLE | 1 |  |  |  |  | 0 |  | TORRINGTON | [15 empty] | 0 |  |  | 0 |  |  | 0
20 |  | C01873D-3 | 3 | 71x6292 |  |  | SEAL, OIL | 2 |  |  |  |  | 0 |  | GARLOCK | [15 empty] | 0 |  |  | 0 |  |  | 0
20 |  | C01873D-3 | 3 | 711829 |  |  | SEAL, OIL | 2 |  |  |  |  | 0 |  | SKF | ALTERNATIVE | [14 empty] | 0 |  |  | 0 |  |  | 0
22 |  | C01873D-3 | 3 | 5100-37-BC |  |  | Retaining Ring | 2 |  |  |  |  | 0 |  | WALDES | [15 empty] | 0 |  |  | 0 |  |  | 0
23 |  | C01873D-3 | 3 | 92845A144 |  |  | Extended-Tip Set Screw 18-8 Stainless Steel, 6-32 Thread, 1/4" Long | 6 | 50 PK |  | 1 | 15.63 | 15.63 | [17 empty] | 0 |  |  | 0 |  |  | 0
24 |  | C01873D-3 | 3 | 9452K19 |  |  | Oil-Resistant Buna-N O-Ring 1/16 Fractional Width, Dash Number 011 | 1 | 100 pk |  | 1 | 4.29 | 4.29 |  |  | Double Check this is suitable replacement | [14 empty] | 0 |  |  | 0 |  |  | 0
25 |  | C01873D-3 | 3 | 92210A108 |  |  | 18-8 Stainless Steel Hex Drive Flat Head Screw 82 Degree Countersink Angle, 4-40 Thread Size, 3/8" Long | 2 | 100 pk |  | 1 | 4.67 | 4.67 | [17 empty] | 0 |  |  | 0 |  |  | 0
26 |  | C01873D-3 | 3 | BR2 |  |  | LUBRICANT | [5 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
30 |  | C01873D-3 | 3 | C03923 | C3 |  | ASSY, 5-TURN TILT POT | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
1 |  | C03923 | 4 | C03922 | C |  |  | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
2 |  | C03923 | 4 | MW12B-5R-10K |  |  |  | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
3 |  | C03923 | 4 | C03920 | C |  |  | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
4 |  | C03923 | 4 | C00931 |  |  |  | 1 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
5 |  | C03923 | 4 | 030-9542-001 |  |  |  | 3 |  |  |  |  | 0 |  |  | CHANGE TO COTS WIRE | [14 empty] | 0 |  |  | 0 |  |  | 0
6 |  | C03923 | 4 | M16878_4BEB0 |  |  |  | A/R |  |  |  |  | 0 |  |  | CHANGE TO COTS WIRE | [14 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C03923 | 4 | M16878_4BEB3 |  |  |  | A/R |  |  |  |  | 0 |  |  | CHANGE TO COTS WIRE | [14 empty] | 0 |  |  | 0 |  |  | 0
8 |  | C03923 | 4 | M16878_4BEB6 |  |  |  | A/R |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C03923 | 4 | 242 |  |  | THREADLOCKER | A/R |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C03923 | 4 | 271 |  |  | THREADLOCKER | A/R |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C03923 | 4 | 04024 |  |  | HARDMAN KALEX | A/R |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C03923 | 4 | 92210a107 |  |  | 18-8 Stainless Steel Hex Drive Flat Head Screw 82 Degree Countersink Angle, 4-40 Thread Size, 5/16" Long | 2 |  |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
3 |  | C01871D | 2 | C01875E-1 | H | [7 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
1 | R-1.3.1 | C01875E-1 | 3 | C01883D | H | [7 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
1 |  | C01883D | 4 | 1000006637 |  |  | 3557K024CR+38/2S 14:1+MG10+X0497 | 1 |  |  | 1 |  | 0 | FAULHABER | Micro-Mo | [15 empty] | 0 |  |  | 0 |  |  | 0
2 |  | C01883D | 4 | C01837B | B |  | Motor Plate | 1 |  |  | 1 |  | 0 | IME | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
3 |  | C01883D | 4 | C01852C | C |  | Modified U-Joint | 1 |  |  | 1 |  | 0 | IME | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
4 |  | C01883D | 4 | 92373A128 |  |  | Roll Pin, 5/64 dia x .63 LG | 1 |  |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
5 |  | C01883D | 4 | 92210A192 |  |  | Screw, 8-32 UNC x .38 LG, FHCS | 2 |  |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
6 |  | C01883D | 4 | 91292A113 |  |  | Screw, M3 x 10mm LG, SHCS | 4 |  |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C01883D | 4 | 242 |  |  | Threadlocker | A/R | EA |  |  | 18.8 | 0 | McMaster | Loctite |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
8 |  | C01883D | 4 | V56ZA2P |  |  | Varistor | 1 |  |  |  | 0.3 | 0 | DigiKey | Littlefuse |  |  | 2025-06-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C01883D | 4 | 03-06-2023 |  |  | Plug | 1 | EA |  |  | 0.2 | 0 | DigiKey | Molex |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C01883D | 4 | 02-06-6103 |  |  | Pin | 2 | EA |  |  | 0.71 | 0 | DigiKey | Molex |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C01883D | 4 | 2328-22UL1429STRRED100 |  |  | Wire, 22 AWG, 19/34 RED | A/R | 100 FT |  |  | 34.25 | 0 | DigiKey | Alpha Wire |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C01883D | 4 | 2328-22UL1429STRBLA100 |  |  | Wire, 22 AWG 19/34 BLK | A/R | 100 FT |  |  | 34.25 | 0 | DigiKey | Alpha Wire |  |  | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
13 |  | C01883D | 4 | 4024 |  |  | A-85 Urethane | A/R |  |  |  | 182.01 | 0 | ELLSWORTH | Hardman |  | 2025-06-18 | [13 empty] | 0 |  |  | 0 |  |  | 0
14 |  | C01883D | 4 | TFE 22 AWG |  |  | Teflon Sleeve | A/R |  |  |  |  | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
15 |  | C01883D | 4 | STFS221 |  |  | 1/2" Shrink Tubing | A/R |  |  |  |  | 0 | MOUSER |  | CAN'T FIND IT | [14 empty] | 0 |  |  | 0 |  |  | 0
16 |  | C01883D | 4 | C01914B | A |  | Tilt Motor Cap | 1 |  |  | 1 |  | 0 | IME | QNA | [15 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
DO NOT WORK ON ITEMS BELOW THIS LINE
2 |  | C01871D | 2 | C01873D-1 |  |  | ASSEMBLY, TILT | 1 | EA |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
3 |  | C01871D | 2 | C01875E-1 |  |  | ASSEMBLY, LANCE DRIVE, .305 LANCE | 1 | EA |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
4 |  | C01871D | 2 | C01874D |  |  | ASSY/WIRING HARNESS | 1 | EA |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
9 |  | C01871D | 2 | P0601560007 |  |  | ASSY, LANCE CABLE | 1 | EA |  |  |  | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
20 |  | C01871D | 2 | 111 |  |  | SEALANT | AR |  |  |  |  | 0 |  | DOW CORNING | [15 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
5 |  | C01871D | 2 | C01824E |  |  | Top Cover | 1 | EA |  |  | 1800 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
6 |  | C01871D | 2 | C01823D |  |  | Cover Gasket | 1 | EA |  |  | 220.85 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
7 |  | C01871D | 2 | C01825B |  |  | Modified Washer | 4 | EA |  |  | 70 | 0 | AXIS | QNA | RFQ sent 6/6, $29.16 from IME | [14 empty] | 0 |  |  | 0 |  |  | 0
8 |  | C01871D | 2 | C01821D |  |  | Cable Retainer | 1 | EA |  |  | 814.85 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
16 |  | C01871D | 2 | C02068B |  |  | Pad, Robot Rear | 1 | EA |  |  | 113.23 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
10 |  | C01871D | 2 | 92196A242 |  |  | Screw, 10-24 UNC x .5 LG, SHCS | 4 | PK 100 |  |  | 13.52 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
11 |  | C01871D | 2 | 92196A106 |  |  | Screw, 4-40 UNC x .25" LG, SHCS | 17 | PK 100 |  |  | 5.74 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
12 |  | C01871D | 2 | 92210A244 |  |  | Screw, 10-24 UNC x .625 LG, FHCS | 3 | PK 100 |  |  | 10.34 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
13 |  | C01871D | 2 | 92196A112 |  |  | Screw, 4-40 UNC x .63" LG, SHCS | 1 | PK 100 |  |  | 6.46 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
14 |  | C01871D | 2 | 91458A113 |  |  | 242 Threadlocker | 1 | ea |  |  | 49.48 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
15 |  | C01871D | 2 | 9452K18 |  |  | O-Ring, 2-010, Buna | 1 | PK 100 |  |  | 2.73 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7Y16M1 |  |  | V Wheel | 2 | EA |  |  | 61.56 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1214540149 |  |  | Mount, Wheel, Robot | 1 | EA |  |  | 308.07 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
17 |  | C01871D | 2 | 94035A519 |  |  | Screw, 4-40 UNC x .16" LG, Shoulder, Socket | 2 | EA |  |  | 3.38 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
18 |  | C01871D | 2 | C02073C |  |  | Tilt Housing Cable Clamp | 1 | EA |  |  | 273.69 | 0 | IME | QNA | RFQ sent 6/6, C02073 in DWG | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
19 |  | C01871D | 2 | 92210A105 |  |  | Screw, 4-40 UNC x .25" LG, FHCS | 1 | PK 100 |  |  | 4.43 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 04024 |  |  | A-85 Urethane | 1 | PK 100 |  |  | 160.11 | 0 | ELLSWORTH | Hardman |  | ELLSWORTH | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | CTA4-IP-60 |  |  | Plug | 1 | EA |  |  |  | 0 | ONLINE COMPONENTS |  |  | floor stock | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 031-9540-000 |  |  | Pins | 11 | EA |  |  | 1.39 | 0 | ONLINE COMPONENTS |  |  | WEB_4 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 225-0070-000 |  |  | Wire Hole Filler Grommet | 6 | EA |  |  | 0.108 | 0 | ONLINE COMPONENTS |  |  | WEB_4 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01801B |  |  | Connector, Rear (Modified) | 1 | EA |  |  | 217.03 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-7T-6 |  |  | Wire, 24 AWG, 7/32 BLU | 1 | 100 FT |  |  | 20 | 0 | ALLIED WIRE |  |  | email quote | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-7T-0 |  |  | Wire, 24 AWG, 7/32 BLK | 1 | 100 FT |  |  | 20.92 | 0 | ALLIED WIRE |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-7T-3 |  |  | Wire, 24 AWG, 7/32 ORN | 1 | 100 FT |  |  | 20.92 | 0 | ALLIED WIRE |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-7T-2 |  |  | Wire, 24 AWG, 7/32 RED | 1 | 100 FT |  |  | 20.92 | 0 | ALLIED WIRE |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-22-19T-0 |  |  | Wire, 22 AWG, 19/34 BLK | 1 | 100 FT |  |  | 26.49 | 0 | ALLIED WIRE |  |  | shopping cart | 2023-07-20 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-22-19T-2 |  |  | Wire, 22 AWG, 19/34 RED | 1 | 100 FT |  |  | 26.49 | 0 | ALLIED WIRE |  |  | shopping cart | 2023-07-20 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | FP-301 3/16" BL 100 |  |  | Heatshrink 3/32" | 1 | 100 FT |  |  | 77 | 0 | NEWARK |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1000006622 |  |  | Motor, Gearhead, Brake | 1 | EA |  |  | 2081.7 | 0 | Micro-Mo |  |  | BUY | 2023-03-13 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01586B |  |  | Gear, Miter, Motor (modified) | 1 | EA |  |  | 321.85 | 0 | CUSTOM | QNA | RFQ sent 6/10, prev $425 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01588D |  |  | Motor Support Bracket | 1 | EA |  |  | 1567.82 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01593B |  |  | Motor Carriage Guide Bar | 2 | EA |  |  | 387.49 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 90145A440 |  |  | Dowel Pin, .093" dia x .63" LG | 1 | PK 50 |  |  | 9.35 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91292A112 |  |  | Screw, M3 X 8 LG, SHCS | 1 | PK 100 |  |  | 5.45 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91771A076 |  |  | Screw, 2-56 UNC x .15 LG, FHP | 1 | PK 100 |  |  | 7.13 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91771A105 |  |  | Screw, 2-56 UNC x .38 LG, FHP | 1 | PK 100 |  |  | 7.5 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | V56ZA2PX2855 |  |  | Varistor | 3 | EA |  |  | 0.39 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1N4004-E3/54 |  |  | Diode | 1 | EA |  |  | 0.29 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 03-06-2042 |  |  | Plug | 1 | EA |  |  | 0.47 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-19T-9 |  |  | Wire, 24 AWG, 19/36 WHT | 1 | 100 FT |  |  | 21.54 | 0 | ALLIED WIRE |  |  | shopping cart | 2023-07-20 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | LC134 BK088 |  |  | Lacing Tape (Roll) | 1 | 30 LB |  |  | 95.57 | 0 | NEWARK |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01596C |  |  | Motor Disengage Block | 1 | EA |  |  | 268.4 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01808B |  |  | Motor Disengage Handle | 1 | EA |  |  | 302.71 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01809C |  |  | Motor Disengage Rod | 1 | EA |  |  | 1072.45 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01598C |  |  | Short Round Link | 1 | EA |  |  | 332.69 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01594B |  |  | Short Link | 1 | EA |  |  | 450.92 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01595B |  |  | Upper Link | 1 | EA |  |  | 450.92 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01597B |  |  | Flat Link | 1 | EA |  |  | 298.11 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 90145A416 |  |  | Dowel Pin, .062" DIA x .31" LG | 1 | PK 100 |  |  | 9.98 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92196A054 |  |  | Screw, 0-80 UNC x .18 LG, SHCS | 1 | PK 100 |  |  | 8.57 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92196A148 |  |  | Screw, 6-32 UNC x .50" LG, SHCS | 1 | PK 100 |  |  | 7.62 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01807B |  |  | Motor Disengage Knob | 2 | EA |  |  | 153.38 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01582C |  |  | Drive Shaft | 1 | EA |  |  | 750 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01584B |  |  | Drive Shaft Miter Gear (Modified) | 1 | EA |  |  | 405.47 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01583B |  |  | Spur Gear (Modified) | 1 | EA |  |  | 345.15 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01585B-1 |  |  | Gear Spacer | 1 | EA |  |  | 120.96 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01585B-2 |  |  | Gear Spacer | 1 | EA |  |  | 70 | 0 | (Possibly IME, but skip) | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01894B |  |  | Drive Shaft Spacer | 1 | EA |  |  | 250 | 0 | AXIS | QNA | RFQ sent 6/6, previosly $159.31 IME | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01912B |  |  | Key | 2 | EA |  |  | 125 | 0 | AXIS | QNA | RFQ sent 6/6, previosly $83.81 IME | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91580A151 |  |  | Internal Retaining Ring | 1 | PK 10 |  |  | 14.85 | 0 | McMaster |  |  | CART | 2025-06-11 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7Y55-PS5025 |  |  | .25 Bore Ball Bearing | 2 | EA |  |  | 5.79 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92311A074 |  |  | Screw, 2-56 UNC x .12LG, Set, Hex Head | 1 | PK 100 |  |  | 13.35 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92311A073 |  |  | Screw, 2-56 UNC x .095 LG, Set, Hex Head | 1 | PK 100 |  |  | 13.86 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91590A113 |  |  | SH-25SS, External Retaining Ring | 1 | PK 10 |  |  | 8.84 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01589C |  |  | Reaction Arm | 6 | EA |  |  | 226.5 | 0 | IME | QNA | RFQ sent 6/6, ask for 6x and 12x | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01591B |  |  | Wheel Pin | 6 | EA |  |  | 74.4 | 0 | IME | QNA | RFQ sent 6/6, ask for 6x and 12x | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01592B |  |  | Stabilizing Wheel | 6 | EA |  |  | 69 | 0 | AXIS | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01590B |  |  | Reaction Arm Pin | 6 | EA |  |  | 148.74 | 0 | IME | QNA | RFQ sent 6/6, ask for 6x and 12x | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7Y55-PSS3118 |  |  | 3/16 Ball Bearing | 6 | EA |  |  | 6.4 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 98410A110 |  |  | Retaining Ring | 1 | PK 100 |  |  | 16.22 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01571C |  |  | Potentiometer Bracket | 1 | EA |  |  | 688.37 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | B1-27 |  |  | .125W .375OD .187ID Ball Bearing | 2 |  |  |  | 10.26 | 0 | Applied Indus. |  | McMaster 3759T54 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01575B |  |  | Idler Shaft | 1 | EA |  |  | 319.65 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01577B |  |  | Idler Spur Gear Modification | 1 | EA |  |  | 262.18 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01573B |  |  | Potentiometer Drive Shaft | 1 | EA |  |  | 522.6 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01572B |  |  | Modified Miter Gear | 1 | EA |  |  | 292.9 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01576B |  |  | POT Idler gear Spacer | 1 | EA |  |  | 155.64 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 20M1765 |  |  | 10 Turn Potentimeter, Loco Pot | 1 | EA |  |  | 226.87 | 0 | NEWARK |  | Do I need this? | 45021 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01580B |  |  | Potentiometer Sleeve | 1 | EA |  |  | 308.93 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01578B |  |  | Knurled Wheel | 1 | EA |  |  | 258.18 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C0240-032-0310-S |  |  | .31 LG .032 Wire .24OD Spring | 1 | pk10 |  |  | 27.33 | 0 | Grainger |  |  | Grainger | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01581B |  |  | POT Spur Gear Modification | 1 | EA |  |  | 309.9 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01579B |  |  | Washer | 1 | EA |  |  | 157.3 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01574B |  |  | Pinion Shaft Modification | 1 | EA |  |  | 510.14 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C03915 |  |  | Bearing Modified | 1 | EA |  |  | 237.36 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | CTA4-IS-60 |  |  | Strip Connector | 1 | EA |  |  |  | 0 | ONLINE COMPONENTS |  |  | floor stock | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 030-9542-001 |  |  | Sockets | 10 | EA |  |  | 1.1 | 0 | ONLINE COMPONENTS |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-19T-6 |  |  | Wire, 24 AWG, 19/36 BLU | 1 | 300 FT |  |  | 25 | 0 | ALLIED WIRE |  | They can dye this for 25$ for 250 feet | shopping cart | 2023-07-20 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-19T-0 |  |  | Wire, 24 AWG, 19/36 BLK | 1 | 100 FT |  |  | 21.54 | 0 | ALLIED WIRE |  |  | shopping cart | 2023-07-20 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1429-24-19T-3 |  |  | Wire, 24 AWG, 19/36 ORN | 1 | 300 FT |  |  | 25 | 0 | ALLIED WIRE |  | They can dye this for 25$ for 250 feet | shopping cart | 2023-07-20 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01567E |  |  | Locomotion Housing | 1 | EA |  |  | 15995 | 0 | AXIS | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01568C-1 |  |  | Wheel Axle | 1 | EA |  |  | 107.55 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01568C-2 |  |  | Wheel Axle | 1 | EA |  |  | 107.55 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01568C-3 |  |  | Wheel Axle | 1 | EA |  |  | 107.55 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01568C-4 |  |  | Wheel Axle | 1 | EA |  |  | 107.55 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01569B-1 |  |  | Wheel Axle Bushing | 2 | EA |  |  | 147.88 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01569B-2 |  |  | Wheel Axle Bushing | 1 | EA |  |  | 80.87 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01569B-3 |  |  | Wheel Axle Bushing | 1 | EA |  |  | 80.87 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01570B |  |  | Flat Guide Wheel | 1 | EA |  |  | 225.16 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01570B |  |  | Flat Guide Wheel | 1 | EA |  |  | 225.16 | 0 | IME | QNA | DUPLICATE | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01587B |  |  | Spacer | 1 | EA |  |  | 142.06 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C0420-063-1000-S |  |  | .420 O.D., .063 Wire, 1.00lb Spring | 1 | pk10 |  |  | 46.36 | 0 | Grainger |  |  | Grainger | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | CL-43-SSPS-1 |  |  | ( Grainger # 2YLG3 ) Spring Plunger | 1 | PK 5 |  |  | 45.75 | 0 | Grainger |  |  | Grainger | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7X 8-C06012 |  |  | .012 Shaft Spacer | 4 | EA |  |  | 1.84 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7X 8-C06014 |  |  | .014 Shaft Spacer | 2 | EA |  |  | 1.91 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7X 8-C06031 |  |  | .031 Shaft Spacer | 1 | EA |  |  | 2 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7X 8-C06063 |  |  | .063 Shaft Spacer | 1 | EA |  |  | 2.06 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 7X 8-C06188 |  |  | .188 Shaft Spacer | 1 | EA |  |  | 2.16 | 0 | SDP |  |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C03922 |  |  | Tilt Potentiometer Bracket | 1 | EA |  |  | 445.16 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | MW12B-5R-10K |  |  | 5 Turn Tilt Potentiometer | 1 | EA |  |  | 100.32 | 0 | MOUSER |  |  | 45021 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C03920 |  |  | Tilt Potentiometer Gear | 1 | EA |  |  | 304.59 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91737A076 |  |  | Screw, 4-40 UNC x .31" LG, FHCS | 1 | PK 100 |  |  | 5.56 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1000006476 |  |  | Cecil IV Tilt Motor | 1 |  |  |  | 930 | 0 | Micro-Mo |  |  | 3/31/2023 | 2023-03-13 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01813C |  |  | Reducer Shaft | 1 | EA |  |  | 1080.3 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01814D |  |  | Tilt Motor Mount | 1 | EA |  |  | 1289.45 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01914B |  |  | Tilt Motor Cap | 1 | EA |  |  | 125 | 0 | AXIS | QNA | RFQ sent 6/6, previously $174.25 IME | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C03244B |  |  | Modified Spur Gear | 1 | EA |  |  | 308.2 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C03245B-2 |  |  | Key | 1 | EA |  |  | 134.41 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91771A148 |  |  | Screw, 6-32 UNC x .50" LG, PHILLIPS, FHMS | 1 | PK 100 |  |  | 7.54 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92196A108 |  |  | Screw, 4-40 UNC x .38" LG, SHCS | 1 | PK 100 |  |  | 4.1 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C03307B |  |  | Tilt Motor Key | 1 | EA |  |  | 378 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01599E-1 |  |  | Tilt Housing | 1 | EA |  |  | 22000 | 0 | AXIS | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01804B |  |  | Modified Spur Gear | 1 | EA |  |  | 327.06 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01822C |  |  | Fixed Guide | 1 | EA |  |  | 2200 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01805B |  |  | Idler Gear Spacer | 2 | EA |  |  | 150 | 0 | AXIS | QNA | RFQ sent 6/6, $113.53 from IME | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01817D |  |  | Assy, Barrel, Tilt | 2 | EA |  |  | 9100 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01818B |  |  | Tilt Bushing | 2 | EA |  |  | 300 | 0 | AXIS | QNA | RFQ sent 6/6, $295 from IME | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01806B |  |  | Idler Shaft Bore Plug | 1 | EA |  |  | 67 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01820B |  |  | Inboard Tilt Bearing Retainer | 1 | EA |  |  | 647.66 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01819B |  |  | Outboard Tilt Bearing Retainer | 1 | EA |  |  | 647.66 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 3408A96 |  |  | Spring Plunger | 3 | EA |  |  | 4.23 | 0 | McMaster |  | DUPLICATE | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | LA025XP0 |  |  | Angular Contact Ball Bearing | 2 | EA |  |  | 312.07 | 0 | MOTION INDUSTRIES |  |  | MA20-890317 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 711829 |  |  | Oil Seal | 2 | EA |  |  | 24.65 | 0 | MOTION INDUSTRIES |  |  | 711829 | 2025-06-17 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 98410A665 |  |  | Retaining Ring | 1 | PK 10 |  |  | 6.28 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 95289A006 |  |  | Screw, 6-32 UNC x .25" LG, Full Dog Set, Hex Head | 1 | PK 100 |  |  | 5.76 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 9452K19 |  |  | O-Ring, 2-011, Buna | 1 | PK 100 |  |  | 4.29 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91771A108 |  |  | Screw, 4-40 UNC x .38" LG, FHP | 1 | PK 100 |  |  | 6.56 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01803C |  |  | Idler Shaft | 1 | EA |  |  | 1900 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 1000006637 |  |  | Gearhead Motor | 1 |  |  |  | 905 | 0 | Micro-Mo |  |  | 3/31/2023 | 2023-03-13 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01837B |  |  | Motor Plate | 1 | EA |  |  | 482.87 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92373A128 |  |  | Roll Pin, 5/64 dia x .63 LG | 1 | PK 100 |  |  | 9.36 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92210A192 |  |  | Screw, 8-32 UNC x .38 LG, FHCS | 1 | PK 100 |  |  | 4.97 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91292A113 |  |  | Screw, M3 x 10 mm LG, SHCS | 1 | PK 100 |  |  | 6 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | M23053/5-108-0 |  |  | 1/2" Shrink Tubing | 1 | 100 FT |  |  | 47 | 0 | HEAT SHRINK SUPPLY |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 02-06-6103 |  |  | Pin | 3 | EA |  |  | 0.63 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | FP-301 1/4" BL 100 |  |  | .12 Shrink Tubing | 1 | 100 FT |  |  | 75.9 | 0 | NEWARK |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | FP-301 1" BL 50 |  |  | .50 Shrink Tubing | 1 | 50 FT |  |  | 91.3 | 0 | NEWARK |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | A 6Z16-057012 |  |  | Belt | 1 | EA |  |  | 2.84 | 0 | SDP |  |  | 3/31/2023 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01857E-1 |  |  | Barrel Spray Manifold Assy. | 1 | EA |  |  | 19912.7845 | 0 | CUSTOM | QNA |  | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 02-06-5103 |  |  | Socket, Molex | 5 | EA |  |  | 0.84 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 03-06-1023 |  |  | Receptacle, Molex | 1 | EA |  |  | 0.25 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 03-06-1032 |  |  | Receptacle, Molex | 1 | EA |  |  | 0.29 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 04024 |  |  | Urethane Adhesive | 1 | PK 100 |  |  | 0 | 0 | ELLSWORTH | Hardman |  | 45016 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01832C |  |  | Manifold Tube Guard | 1 | EA |  |  | 1850 | 0 | AXIS | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01829E |  |  | Inner Guide | 1 | EA |  |  | 2900 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01828D |  |  | Lance Drive Barrel | 1 | EA |  |  | 3200 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01830D |  |  | Lance Drive Cap | 1 | EA |  |  | 1900 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01840B |  |  | Release Bar Block | 1 | EA |  |  | 293 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01842B |  |  | Vertical Release Bar | 1 | EA |  |  | 450 | 0 | CUSTOM | QNA | RFQ sent 6/10, IME RFQ sent 6/6, previously $544 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01839C |  |  | Outer Release Bar | 1 | EA |  |  | 559.81 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01845C-1 |  |  | Drive Release Slide Plate | 1 | EA |  |  | 1900 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01845C-2 |  |  | Drive Release Slide Plate | 1 | EA |  |  | 1900 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01841B |  |  | Cap Rod | 1 | EA |  |  | 120.5 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01831C |  |  | Outer Guide | 1 | EA |  |  | 2700 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01836B |  |  | Motor Support Plate | 1 | EA |  |  | 1200 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | B6-13 |  |  | Spacer | 1 | EA |  |  | 2.34 | 0 | PIC |  |  | WEB_31 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01835B |  |  | Tube Bracket | 1 | EA |  |  | 311.58 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01833B |  |  | Tube Clamp | 1 | EA |  |  | 308.09 | 0 | IME | QNA | RFQ sent 6/6 | 5635 | 2023-04-05 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01843B |  |  | Release Bar (RH) | 1 | EA |  |  | 890 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01844B |  |  | Release Bar (LH) | 1 | EA |  |  | 890 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01834D |  |  | Edge Plate | 1 | EA |  |  | 2400 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01827C-1 |  |  | Motor Support | 1 | EA |  |  | 2400 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01827C-2 |  |  | Motor Support | 1 | EA |  |  | 2400 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | HL3-T21 |  |  | 3/8 FPT Plug | 1 | EA |  |  | 14.49 | 0 | Applied Indus. |  |  | HL3-T21 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92210A151 |  |  | Screw, 6-32 UNC x .75" LG, FHSC | 1 | PK 100 |  |  | 5.13 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92196A302 |  |  | Screw, 4-40 UNC x 1.25" LG, SHCS | 1 | PK 100 |  |  | 7.18 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92210A194 |  |  | Screw, 8-32 UNC x .5 LG, FHHS | 1 | PK 100 |  |  | 5.51 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 91771A106 |  |  | Screw, 4-40 UNC x .25" LG, FHP | 1 | PK 100 |  |  | 5.4 | 0 | McMaster |  |  | McMaster-Carr 1 | 2023-07-18 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92210A148 |  |  | Screw, 6-32 UNC x .50" LG, FHHS | 1 | PK 100 |  |  | 4.32 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92210A150 |  |  | Screw, 6-32 UNC X .62" LG, FHHS | 1 | PK 100 |  |  | 4.69 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01826D-1 |  |  | Orifice | 4 | EA |  |  | 250 | 0 | AXIS | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01826D-2 |  |  | Orifice | 2 | EA |  |  | 275 | 0 | AXIS | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01826D-3 |  |  | Orifice | 2 | EA |  |  | 275 | 0 | AXIS | QNA | RFQ sent 6/6 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01884D |  |  | Assembly, Worm Drive | 1 | EA |  |  | 21495 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01847B |  |  | Potentiometer Bracket | 1 | EA |  |  | 425 | 0 | CUSTOM | QNA | RFQ sent 6/10, IME RFQ sent 6/6, previously $297.58 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01856B |  |  | Large Potentiometer Pulley (SDP-SI) | 1 | EA |  |  | 375 | 0 | CUSTOM | QNA | RFQ sent 6/10, IME RFQ sent 6/6, previously $378.99 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C01852C |  |  | Modified U-Joint | 1 | EA |  |  | 1235.125 | 0 |  | QNA | IME RFQ sent 6/6, previously $1453 | [14 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 3700S-1-103L |  |  | Potentiometer, LD, 10k, 5% | 1 | EA |  |  | 123.07 | 0 | MOUSER |  |  | 45021 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 03-06-2023 |  |  | Plug, Molex | 3 | EA |  |  | 0.26 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 02-06-6103 |  |  | Pin | 8 | EA |  |  | 0.63 | 0 | MOUSER |  |  | shopping cart | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92196A150 |  |  | Screw, 6-32 UNC x .62" LG, SHCS | 1 | PK 100 |  |  | 5.66 | 0 | McMaster |  |  | McMaster-Carr 1 | [13 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92383A202 |  |  | SPRING PIN 3/32 x .38LG, SS | 3 | 100 pk |  |  | 9.59 | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92383A206 |  |  | SPRING PIN 3/32 x .63LG, SS | 4 | 100 pk |  |  | 12.54 | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | 92383A204 |  |  | SPRING PIN 3/32 x .50LG, SS | 7 | 100 pk |  |  | 11.16 | 0 | McMaster | [16 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C02660B-1 |  |  | MOTOR BRACKET SHIM | 1 | EA |  |  | 125 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C02660B-2 |  |  | MOTOR BRACKET SHIM | 1 | EA |  |  | 125 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C02660B-3 |  |  | MOTOR BRACKET SHIM | 1 | EA |  |  | 125 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C02660B-4 |  |  | MOTOR BRACKET SHIM | 1 | EA |  |  | 125 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
|  |  |  | C02660B-5 |  |  | MOTOR BRACKET SHIM | 1 | EA |  |  | 125 | 0 | CUSTOM | QNA | RFQ sent 6/10 | 403568 | 1/26/23 | [12 empty] | 0 |  |  | 0 |  |  | 0
0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0
[13 empty] | 0 | [17 empty] | 0 |  |  | 0 |  |  | 0

## Sheet2
Customer Item Level
Subassembly Level